## Task Backlog 2016-04
TASK ID | Project/Task/Issue Type | Task Title | Description | Priority 1- Urgent; 2 -High 3-Medium 4 -Low | Est in days | Status
#001 | Enhancement | Add VDC Filter in Add Group to training | Added dropdown for VDC Filter in Add Group to training | 1 | 1 | in QC
#002 | Enhancement | Add VDC Filter in Add Individual to training | Added dropdown for VDC Filter in Add Training to training | 1 | 1 | in QC
#003 | DEV Testing | Testing Add VDC Filter in Group/Individual to training | QC Testing for VDC Filter in in training |  | 1 | in QC
#004 | QC Testing | Testing Add VDC Filter in Group/Individual to training | QC Testing for VDC Filter in in training |  | 1 | in QC
#005 | Enhancement | Search Form for existing recipient from KISAN to Add to Grantee | Creating Search form to identify Individual(Farmer Recipient) using field provided and flagged as population for specific Grantee Partner | 1 | 3 | in QC
#006 | Enhancement | Add new recipient to Grantee if KISAN recipient not found | IF the farmer is not in the existing population then it needs to be added | 1 | 4 | in QC
#007 | Enhancement | Add Active/Inactive in Training Type Lookup and Sort by Name | Add Active/Inactive in Training Type Lookup and sort Training Type by Name | 1 | 1 | in QC
#008 | DEV Testing | Testing for Search form for existing recipient from KISAN to Add to Grantee | Testing for Search form for existing recipient from KISAN to add to Grantee,If not found then add new recipient to Grantee | 1 | 2 | in QC
#009 | QC Testing | Testing for Search form for existing recipient from KISAN to Add to Grantee | Testing for Search form for existing recipient from KISAN to add to Grantee,If not found then add new recipient to Grantee | 1 | 1 | in QC
#010 | Enhancement | Flag Group which has not taken a SINGLE Training | Check if group has taken any training and flag the group if it has taken training | 2 | 1.5 | in QC
#011 | DEV Testing | Testing to check the flag for group taking any training | Testing to check the flag for group taking any training | 2 | 1 | in QC
#012 | Request | User Guide with prerequisites for Desktop Version of WIKISAN | Preparing user guide with prerequisites for Desktop Version of WIKISAN | 2 | 2 | in QC
#013 | Improvement | Disable Add Individual to Training | Check if individual is added to training without creating group and resolve within group then Disable Add Individual to Group | 1 | 2.5 | in QC
#014 | Enhancement | Change existing Organization to Grantee | Convert existing KISAN Organization to grantee | 1 | 1.5 | in QC
#015 | Enhancement | Add new Grantee Organization | Create new Form for Grantee | 1 | 1.5 | in QC
#016 | DEV Testing | Testing Disable Add Individual to Training, Add existing KISAN Organization or New Grantee | Testing to check working of new KISAN Grantee Form and converting existing Organization to Grantee | 1 | 1.5 | in QC
#017 | QC Testing | Testing Disable Add Individual to Training, Add existing KISAN Organization or New Grantee | Testing to check working of new KISAN Grantee Form and converting existing Organization to Grantee | 1 | 1 | in QC
#018 | Enhancement | Grantee View and List | Add Grantee View Form and List form to search | 1 | 3 | in QC
#019 | Enhancement | Add Grantee Recipient List | Add Grantee Recipient List for farmers who are associated with grantee | 1 | 1.5 | in QC
#020 | DEV Testing | Testing for Grantee View, Grantee List and Grantee Recipient List | Testing for functionality for Grantee View, Grantee List and Grantee Recipient List | 1 | 1.5 | in QC
#021 | QC Testing | Testing for Grantee View, Grantee List and Grantee Recipient List | Testing for functionality for Grantee View, Grantee List and Grantee Recipient List | 1 | 1 | in QC
#022 | Enhancement | Add Grantee Menu in KISAN Menu List | Add Grantee Menu in KISAN Menu List | 3 | 0.5 | in QC
#023 | Bug Fix | Show Active Group/Individuals for Data Entry, all for Program Admin, Site Admin in Reports | Show Active Groups/Individuals for Data Entry, all data for Program Admin and Site Admin in Reports | 2 | 2.5 | in QC
#024 | DEV Testing | Testing for checking reports for Group/Recipients for Active/Inactive data for different roles | Testing for checking reports for Group/Recipients for Active/Inactive data for different roles | 1 | 1.5 | in QC
#025 | QC Testing | Testing for checking reports for Group/Recipients for Active/Inactive data for different roles | Testing for checking reports for Group/Recipients for Active/Inactive data for different roles | 1 | 1 | in QC
#026 | Enhancement | Add fields in Grantee Recipients | Add additional fields in grantee recipients | 1 | 1.5 | To Start
#027 | Enhancement | [New Form] Grantee Group | Form to add new group to Grantee | 1 | 2 | To Start
#028 | Enhancement | Grantee Group List | Add Grantee Group List | 1 | 1 | To Start
#029 | Enhancement | Add Existing Group to Grantee | Add Existing Group to Grantee | 1 | 1.5 | To Start
#030 | Testing | Testing for new Grantee Group, Add Existing Group to Grantee and Grantee Group List | Test functionalities for all updates | 1 | 1 | To Start
#031 | Enhancement | [New Form] Grantee Training | Form to add new training to Grantee | 1 | 2.5 | To Start
#032 | Enhancement | Grantee Training List | Add Grantee Training List | 1 | 1.5 | To Start
#033 | Enhancement | Add Existing Training to Grantee | Add Existing Training to Grantee | 1 | 1.5 | To Start
#034 | Testing | Testing for new Grantee Training, Add Existing Training to Grantee and Grantee Training List | Test functionalities for all updates | 1 | 1 | To Start
#035 | Enhancement | Create grantee user-group | Create user group specific for grantee strictly | 1 | 3 | To Start
#036 | Testing | Testing for grantee user-group | Testing for grantee user-group | 1 | 1.5 | To Start
#037 | Improvement | Disable KISAN entities for grantee for EDIT/DELETE | To disable Grantee Organization to EDIT/DELETE KISAN Entities | 1 | 2.5 | To Start
#038 | Improvement | Disable KISAN Menu for grantee | To disable KISAN Menu for grantee | 2 | 1 | To Start
#039 | Maintenance | Bug-fix and Maintenance | Fix users for single login irrespective of browsers, Redefine ID Generation Function including logged-in user ID | 2 | 6
#040 | Testing | Testing for user permission for Grantee user group | Testing for user permission for grantee user-group | 1 | 1.5 | To Start
|  |  |  | Total | 67.5

## Q1 2016 Backllog (new)
Sno | Request Title | Request Detail | Priority | UpendraP | SujitB | Status | Remarks
1 | Filter with VDC in All Reports | 1. Add VDC to Summary Query: Preselect District and VDC in the Summary Report. Provide Results with District and VDC. Currently reporting t is only with Districts 2. Report Module | 2 | 1 | 3 | Not Started
2 | Filter with VDC in All Search List including Forms | 1. VDC Filter in Add Group to training; 2. VDC Filter in Add Individual to training; 3. Disable Add Individual to Group) - See #11 | 1 | 1 | 2 | 4.3.1 | Filter with VDC - 1. Add Group to Training (Feb 10) 2. Add Individual to Training Disable feature to add individual within the group? Yes (Feb 10)
3 | Search Form for Existing Recipient and Add New Recipient according to Grantee (Private Sector Partner/Organization) | Create Search form to identify Individual (Farmer Recipient) using field provided and flagged as Population for specific Grantee Partner. ¦If the farmer is not in the existing population then it needs to be added. Flag Indentified Recipients with Grantee Flag | 1 | 2 | 4 | 4.3.1
4 | Add Active Inactive in all Look-ups and Sort by Name | Add Active/Inactive in all Roll-up and Sort by Name; There are around 20+ Look ups. | 1 | 0.5 | 1 | 4.3.1 | Only for training rollups got (Feb 10)
5 | Flag Group which has not taken a SINGLE Training | Flag the if Group has not participated in at least one training. | 1 | 0.5 | 1 | 4.3.1
6 | Tag Groups | Tag Groups: Create Tags to Group as requirements on the Tag is provided : Irrigation Tag Access to Finance Tag | 3 |  |  | Not Started | Under discssion
7 | CRM for Private Agro Firms | Identify couple of open source CRM for Private Agro Firms and provide demo | 3 | 1 | 2 | Started
8 | Desktop Version for WIKISAN | Create User Guide with prerequisites and make installation and support of installations | 3 | 1 | 2 | Started
9 | Survey Support | Survey Support | 2 | 0.5 | 1 | Started
10 | Irrigation Module | Irrigation Module | 3 |  |  | Not Started | Under discssion
11 | Disable Add Individual to Training | Check if individual is added to training without creating group and resolve within group then Disable Add Individual to Group | 1 | 0.5 | 1.5 | 4.3.1
12 | Add Training count in Group and Individual Listing | Provide Training count to the list of Group and Individual | 3 |  |  | Not Started | Feasiblity - Performance
13 | Active only needs to be shown in all reports | Active/Inactive Individual/Group need to be reflected in reports | 1 | 0.5 | 1 | 4.3.1 | Bug
|  | Total Days |  | 8.5 | 18.5

## New Q1 2016 Back Log - Discuss (hidden)
Wikisan AMC:2016(Q1): New Requirements
| Request Title | Request Detail | Priority | UpendraP | SujitB | Status | Remarks
1 | Filter with VDC in All Reports | 1. Add VDC to Summary Query: Preselect District and VDC in the Summary Report. Provide Results with District and VDC. Currently reporting t is only with Districts 2. Report Module | 2 |  |  | Not Started
2 | Filter with VDC in All Search List including Forms | 1. VDC Filter in Add Group to training; 2. VDC Filter in Add Individual to training; 3. Disable Add Individual to Group) - See #11 | 1 | 1 | 2 | 4.3.1 | Filter with VDC - 1. Add Group to Training (Feb 10) 2. Add Individual to Training Disable feature to add individual within the group? Yes (Feb 10)
3 | Search Form for Existing Recipient and Add New Recipient according to Grantee (Private Sector Partner/Organization) | Create Search form to identify Individual (Farmer Recipient) using field provided and flagged as Population for specific Grantee Partner. ¦If the farmer is not in the existing population then it needs to be added. Flag Indentified Recipients with Grantee Flag | 1 | 2 | 4 | 4.3.1
4 | Add Active Inactive in all Look-ups and Sort by Name | Add Active/Inactive in all Roll-up and Sort by Name; There are around 20+ Look ups. | 1 | 0.5 | 2 | 4.3.1 | Only for training rollups got (Feb 10)
5 | Flag Group which has not taken a SINGLE Training | Flag the if Group has not participated in at least one training. | 1 | 0.5 | 2 | 4.3.1
6 | Tag Groups | Tag Groups: Create Tags to Group as requirements on the Tag is provided : Irrigation Tag Access to Finance Tag | 2 |  |  | Not Started | How about for Individuals
7 | CRM for Private Agro Firms | Identify couple of open source CRM for Private Agro Firms and provide demo | 3 | 1 | 2 | Started
8 | Desktop Version for WIKISAN | Create User Guide with prerequisites and make installation and support of installations | 3 | 1 | 2 | Started
9 | Survey Support | Survey Support | 2 | 0.5 | 1 | Started
10 | Irrigation Module | Irrigation Module |  |  |  | Not Started
11 | Disable Add Individual to Training | Check if individual is added to training without creating group and resolve within group then Disable Add Individual to Group | 1 | 1 | 2 | 4.3.1
12 | Add Training count in Group and Individual Listing | Provide Training count to the list of Group and Individual | 3 |  |  | Not Started | Feasiblity - Performance
13 | Active only needs to be shown in all reports | Active/Inactive Individual/Group need to be reflected in reports | 1 | 0.5 | 1 | 4.3.1 | Bug
|  | Total Days |  | 8 | 18 | Total

## Release -3.4
Wikisan AMC: 2015 (Q3/Q4) - 2016(Q1/Q2). | UpendraP | SujitB | Priority | Status | Remarks
1. New Requirements -- Entry System Modules and Reports
· Entry System for Grantee Beneficiaries, similar to individual module (New) | 2 | 4 |  | Not Started
· Grantee Reports, 5 reports (New) | 2 | 5 |  | Not Started
· Framework for error handling and access management such as using email to inform system administrator on exceptions and errors (New) | 2 | 4 |  | Not Started
· Training Reports, # of Reports= 5 (New) | 3 | 7 |  | Not Started
· Export to Excel function (New) | 1.5 | 4 | 1 | Prod 3.4
· Better usability of Pagination (Enhancement) - Customizable # of records listing in grid, not greater than 100 per page (Enhancement) | 1.5 | 3.5 | 1 | Prod 3.4
· Outcome 3 report generation, #2 (New) | 1 | 3 |  | Not Started
· Outcome 4 report generation, #2 (New) | 1 | 3 |  | Not Started
· Outcome 5 report generation, #2 (New) | 1 | 3 |  | Not Started
· Drill Down Reports, #5 (New) | 2.5 | 6 |  | Not Started
Total Days | 17.5 | 42.5 |  | Total
2. Enhancementof Existing Entry System Modules and Reports
· Search Feature within dropdowns combo box (District, VDC, Group) of Window of Organization, Group, Individual and Training (Enhancement) | 2 | 4 |  | Not Started
· Filter by searching individual columnin all grids of all modules. | 3 | 8 |  | Not Started
· Custom Columns on the Search Page Table Grid for 4 primary modules for administrator to choose the columns (Enhancement) -- nice to have, defer, |  |  |  | Not Started | 4+10 = 14
· Embed URL thru Configuration and SSL at the time of renewal with hosting company (Enhancement) | 1 | 1 |  | Not Started
· Duplicate Handling with records already having references (Maintenance) | 1 | 3 | 1 | Prod 3.4
· Outcome Report 2 should have the following selection box: Ethnic, Religion and Vulnerable groups (Enhancement) | 0.5 | 1 |  | Not Started
· System Maintenance Support (Maintenance) | 1.5 | 0.5 | 1 | On-going | 35%
· Support for General Bug Fix (Maintenance + Unplanned work) | 3 | 7 | 1 | On-going | 35%
· Update Group form such as to tag if the group is a seed group, plus two additional tags (Enhancement) | 1 | 2 |  | Not Started
· Update Training form – additional 3 tags (Enhancement) | 1 | 2 |  | Not Started
· Flag for Natural Calamity in Group (New) | 1 | 3 | 1 | Prod
· Group and Training with Date selection (Enhancement) | 0.5 | 1 | 1 | Prod
Total Days | 15.5 | 32.5 |  | Total
3. Maintenance of Existing Entry System Modules and Reports
· IT and Web Application Security such as Penetration Test, check and resolve vulnerabilities (Maintenance) | 2 | 5 |  | Not Started
· Performance Analysis and Optimization: check, data analysis and resolve and optimize SQL and PHP request handling, including looking at database size (Maintenance) | 3 | 7 |  | Not Started
· Training Search list search by Beneficiary type and training type (Enhancement) | 0.5 | 1.5 | 1 | Prod
· Bug Fix - Summary Report (Maintenance) | 0.5 | 2 |  | Not Started
· Tag Group/Beneficiaries Inactive (Enhancement) | 1 | 2 | 1 | Prod
· Summary Report to include date, better usability of UI (Enhancement) | 0.5 | 2 | 1 | Prod
Total Days | 7.5 | 19.5 |  | Total
4. Training
· Provide 3 days training to the new GIS and DQA Expert in system administration | 2 | 1 |  | Total
Q2 Deliverable | 2.5 | 6.5 | 1 | Prod
Overall Total Days | 45 | 102 |  | G Total
In Prod before contract | 5.5 | 16.5
In Prod 3.4 | 5 | 13.5
In Prod 3.4 | 4 | 4 | Deployment and IT work
| 14.5 | 34
| 8 | 8
| 116 | 272

## Product Backlog and Plan
Wikisan AMC: 2015 (Q3/Q4) - 2016(Q1/Q2). | UpendraP | SujitB | Priority | Status | Remarks
1. New Requirements -- Entry System Modules and Reports
· Entry System for Grantee Beneficiaries, similar to individual module (New) | 2 | 4 |  | Not Started
· Grantee Reports, 5 reports (New) | 2 | 5 |  | Not Started
· Framework for error handling and access management such as using email to inform system administrator on exceptions and errors (New) | 2 | 4 |  | Not Started
· Training Reports, # of Reports= 5 (New) | 3 | 7 |  | Not Started
· Export to Excel function (New) | 1.5 | 4 | 1 | Prod 3.4 | 1.5+4
· Better usability of Pagination (Enhancement) - Customizable # of records listing in grid, not greater than 100 per page (Enhancement) | 1.5 | 3.5 | 1 | Prod 3.4 | 1.5+3.5
· Outcome 3 report generation, #2 (New) | 1 | 3 |  | Not Started
· Outcome 4 report generation, #2 (New) | 1 | 3 |  | Not Started
· Outcome 5 report generation, #2 (New) | 1 | 3 |  | Not Started
· Drill Down Reports, #5 (New) | 2.5 | 6 |  | Not Started
Total Days | 17.5 | 42.5 |  | Total
2. Enhancementof Existing Entry System Modules and Reports
· Search Feature within dropdowns combo box (District, VDC, Group) of Window of Organization, Group, Individual and Training (Enhancement) | 2 | 4 |  | Not Started
· Filter by searching individual columnin all grids of all modules. | 3 | 8 |  | Not Started
· Custom Columns on the Search Page Table Grid for 4 primary modules for administrator to choose the columns (Enhancement) -- nice to have, defer, |  |  |  | Not Started | 4+10 = 14
· Embed URL thru Configuration and SSL at the time of renewal with hosting company (Enhancement) | 1 | 1 |  | Not Started
· Duplicate Handling with records already having references (Maintenance) | 2 | 6 | 1 | Prod 3.4
· Outcome Report 2 should have the following selection box: Ethnic, Religion and Vulnerable groups (Enhancement) | 0.5 | 1 |  | Not Started
· System Maintenance Support (Maintenance) | 4 | 4 | 1 | On-going | 1+1
· Support for General Bug Fix (Maintenance + Unplanned work) | 7 | 30 | 1 | On-going | 2+4
· Update Group form such as to tag if the group is a seed group, plus two additional tags (Enhancement) | 1 | 2 |  | Not Started
· Update Training form – additional 3 tags (Enhancement) | 1 | 2 |  | Not Started
· Flag for Natural Calamity in Group (New) | 1 | 3 | 1 | Prod
· Group and Training with Date selection (Enhancement) | 0.5 | 1 | 1 | Prod
Total Days | 23 | 62 |  | Total
3. Maintenance of Existing Entry System Modules and Reports
· IT and Web Application Security such as Penetration Test, check and resolve vulnerabilities (Maintenance) | 2 | 5 |  | Not Started
· Performance Analysis and Optimization: check, data analysis and resolve and optimize SQL and PHP request handling, including looking at database size (Maintenance) | 3 | 7 |  | Not Started
· Training Search list search by Beneficiary type and training type (Enhancement) | 0.5 | 1.5 | 1 | Prod
· Bug Fix - Summary Report (Maintenance) | 0.5 | 2 |  | Not Started
· Tag Group/Beneficiaries Inactive (Enhancement) | 1 | 2 | 1 | Prod
· Summary Report to include date, better usability of UI (Enhancement) | 0.5 | 2 | 1 | Prod
Total Days | 7.5 | 19.5 |  | Total
4. Training
· Provide 3 days training to the new GIS and DQA Expert in system administration | 2 | 1 |  | Total
Q2 Deliverable | 2 | 7 |  | Prod
Overall Total Days | 52 | 132 |  | G Total
In Prod before contract | 5.5 | 16.5
In Prod 3.4 | 5 | 13.5
In Prod 3.4 | 4 | 4 | Deployment and IT work
| 14.5 | 34
| 8 | 8
| 116 | 272

## 30 Sep Updates (hidden)
Maintenance
Log when deleted or edited or added
Summary Query - date Usability
No sorting in Action
Send to Excel in Right most header column which has action
Send to excel with number as string
Send to excel with order as in list
Show Records - 10, 25, 50, 100

## Activity Sheet 3.4 (hidden)
| Day of Week | Activity Symbol |  | *Time of Departure | *Time of Arrival | Brief Description of Activity | Official Hours (2) | Activity (3)
Date |  |  | Location
2015-09-25 | Fri | Duplicates – Report Data Analysis |  |  |  | Maintenance -Analyzing data for entities including duplicate and association on QC | 2 | D
2015-09-25 | Fri | Feature Discussions |  |  |  | Feature Discussions with Stakeholders | 2 | D
2015-09-26 | Sat | Duplicates – Report Data Analysis |  |  |  | Maintenance - Analyzing data for entities including duplicate and association on Stage | 3 | D
2015-09-27 | Sun | Duplicates and Report and Data Analysis |  |  |  | Maintenance - Performance, Validation and QC | 3 | D
2015-10-01 | Thu | Performance check on Stage and Production(QC) after changes |  |  |  | Maintenance - Analyzing the performance after all changes on Stage and Production(QC) | 2 | D
2015-10-02 | Fri | Maintenance - Performance check on Stage and Production after changes |  |  |  | Analyzing the performance after all changes on Stage and Production | 2 | D
2015-10-03 | Sat | Design Requirement Analysis - Flag natural calamity in Individual |  |  |  | Set status for individual affected with natural calamities like flood and earthquake | 3 | D
2015-10-04 | Sun | QC - Flag natural calamity in Group in Dev Environment |  |  |  | Data Analysis - QC and testing | 3 | D
2015-10-08 | Thu | Meeting on Requirements and delivery - clarifications on backlog |  |  |  | Preparation on setup flag status for natural calamity for individual and group for testing | 3 | D
2015-10-09 | Fri | Requirement Analysis and Design Tag Active/Inactive for Groups Overall delivery discussion |  |  |  | Set flag for Active/Inactive for All entities in Wikisan Overall delivery discussion | 3 | D
2015-10-10 | Sat | QC - Training Search list by training type and beneficiary type |  |  |  | QC and testing | 3 | D
2015-10-11 | Sun | Dev - QC - Group and Training Report with Date Selection - search list by training type and beneficiary type |  |  |  | QC Regression - Adding training | 2 | D
2015-10-11 | Sun | Report with date selection, training search list with beneficiary type and training type for testing |  |  |  | QC of Group/Training - Deployment - QC Deployment and Testing | 3 | D
2015-10-17 | Sat | QC - Tag Active/Inactive for Groups |  |  |  | QC and Testing with Dataset inputs | 4 | D
2015-10-22 | Thu | QC : Date in Training and Organization Summary Query |  |  |  | QC - Regression | 2 | D
2015-10-23 | Fri | Testing : Date in Training and Organization Summary Query, The Summary Query report dashboard is separated for entities to enhance the performance |  |  |  | Performance Tuning - Solutions and POC | 4 | D
2015-10-24 | Sat | QC Testing and Overall with new Dataset from Production |  |  |  | Testing and Overall with new Dataset from Production | 2 | D
2015-10-24 | Sat | Pagination UI |  |  |  | Deployment of Summary Query Report for testing | 3 | D
2015-10-25 | Sun | Pagination UI |  |  |  | Requirements/Design of Training add to Group (Mock-up) Requirements/Design | 4 | D
2015-10-26 | Mon | Pagination UI |  |  |  | QC - Training add to Group /Org/Training/Leverage | 4 | D
2015-10-29 | Thu | Pagination UI |  |  |  | Revisits with Different browser testing of Training add to Group (Mock-up) Requirements/Design | 3 | D
2015-10-30 | Fri | Pagination UI |  |  |  | Testing and issues communications with developer and Kisan | 3 | D
2015-10-31 | Sat | Pagination UI |  |  |  | Overalll analysis Pagination for better usability for testing | 4 | D
2015-11-01 | Sun | Export to Excel functionality |  |  |  | Requirements/Design with Mock-up | 3 | D
2015-11-02 | Mon | Export to Excel functionality |  |  |  | Solutions PoC | 3 | D
2015-11-05 | Thu | Export to Excel functionality |  |  |  | POC Applying Export to Excel functionality in Organization | 2 | D
2015-11-06 | Fri | Export to Excel functionality in Individual |  |  |  | Applying Export to Excel functionality in Training | 2 | D
2015-11-07 | Sat | Export to Excel functionality in Individual |  |  |  | QC and Testing | 3 | D
2015-11-08 | Sun | Deployment - QC Deployment and Testing |  |  |  | QC and Testing | 3 | D
2015-11-09 | Mon | Add Search by Entity ID in Search list of entities |  |  |  | Requirements/Design with Mock-up | 2 | D
2015-11-09 | Mon | Duplicate issue |  |  |  | Resolutions token and session handling | 2 | D
2015-11-12 | Thu | Duplicate issue |  |  |  | Applied token verification and validation dev env | 2 | D
2015-11-13 | Fri | Duplicate issue |  |  |  | Applied token verification and validation dev env | 3 | D
2015-11-14 | Sat | Duplicate issue |  |  |  | Testing and validation | 3 | D
2015-11-15 | Sun | Duplicate issue |  |  |  | Testing and validation | 3 | D
2015-11-16 | Mon | All features finalize : QC Deployment and Testing |  |  |  | All features finalize : QC Deployment and Testing | 3 | D
2015-11-16 | Mon | New feature discussion on third party data |  |  |  | Disucssion | 1 | D
2015-11-16 | Mon | All features finalize : QC Deployment and Testing |  |  |  | All features finalize : QC Deployment and Testing in Stage - Issue finding | 3 | D
2015-11-21 | Sat | All features finalize : QC Deployment and Testing |  |  |  | All features finalize : QC Deployment and Testing in Stage - verfication and Regression | 4 | D
2015-11-22 | Sun | All features finalize : QC Deployment and Testing |  |  |  | All features finalize : QC Deployment and Testing in Stage: Smoke testing | 5 | D
2015-11-23 | Mon | All features finalize : QC Deployment and Testing |  |  |  | All features finalize : QC Deployment and Testing in Stage | 2 | D
[6 empty] | TOTAL | 116
14.5